## m3-before
WIRED BRAIN COFFEE
WEEKLY STATUS REPORT
Date: July 7, 2023
OPEN ISSUES |  | BUDGET
Severity | Number of Issues | Month | Planned | Actual
Critical | 2 | 2023-01-01 | 40000 | 38264
High | 1 | 2023-02-01 | 45000 | 46550
Medium | 5 | 2023-03-01 | 65000 | 62345
Low | 8 | 2023-04-01 | 38000 | 44950
|  | 2023-05-01 | 30000 | 58200
|  | 2023-06-01 | 40000
TASK STATUS
Status | Number of Tasks
Not Started | 13 | TOTAL | 258000 | 250309
In Progress | 40
Completed | 87
Planned & Actual Budget.
January-June 2023
Overspend due to prepayment for the june event swag
OPEN ISSUES
BUDGET
TASK STATUS

## m3-after
WEEKLY STATUS REPORT
DATE: July 7, 2023
OPEN ISSUES |  | BUDGET
Severity | Number of Issues | Month | Planned | Actual
Critical | 2 | 2023-01-01 | 40000 | 38264
High | 1 | 2023-02-01 | 45000 | 46550
Medium | 5 | 2023-03-01 | 65000 | 62345
Low | 8 | 2023-04-01 | 38000 | 44950
|  | 2023-05-01 | 30000 | 58200
|  | 2023-06-01 | 40000
TASK STATUS
Status | Number of Tasks
Not Started | 13 | TOTAL | 258000 | 250309
In Progress | 40
Completed | 87
Planned and Actual Budget, January-June 2023
Overspend due to prepayment for June event swag
OPEN ISSUES
TASK STATUS
BUDGET

## m4-before
WEEKLY STATUS REPORT
DATE: July 7, 2023
OPEN ISSUES |  | BUDGET
Severity | Number of Issues | Month | Planned | Actual
Critical | 2 | 2023-01-01 | 40000 | 38264
High | 1 | 2023-02-01 | 45000 | 46550
Medium | 5 | 2023-03-01 | 65000 | 62345
Low | 8 | 2023-04-01 | 38000 | 44950
|  | 2023-05-01 | 30000 | 58200
|  | 2023-06-01 | 40000
TASK STATUS
Status | Number of Tasks
Not Started | 13 | TOTAL | 258000 | 250309
In Progress | 40
Completed | 87
Planned and Actual Budget, January-June 2023
Overspend due to prepayment for June event swag
OPEN ISSUES
TASK STATUS
BUDGET

## m4-after
WEEKLY STATUS REPORT
DATE: July 7, 2023
OPEN ISSUES |  | BUDGET
Severity | Number of Issues | Month | Planned | Actual
Critical | 2 | 2023-01-01 | 40000 | 38264
High | 1 | 2023-02-01 | 45000 | 46550
Medium | 5 | 2023-03-01 | 65000 | 62345
Low | 8 | 2023-04-01 | 38000 | 44950
|  | 2023-05-01 | 30000 | 58200
|  | 2023-06-01 | 40000
TASK STATUS
Status | Number of Tasks
Not Started | 13 | TOTAL | 258000 | 250309
In Progress | 40
Completed | 87
OPEN ISSUES
TASK STATUS
BUDGET

## Sheet1
Total Number of Tasks | 28
28 Task Done